## Slide 1: Envision SFA
developing the next strategic plan…

## Slide 2: Strategic Planning Process
The chance we will have over the next several months to:
take an in-depth look look at the opportunities and challenges before us as we,
develop a plan to provide guidance on how to achieve a sustainable and successful future.

## Slide 3: End Result
The plan that emerges should:
  document aspirational institutional goals,
  present clear strategies directed toward achievement of these goals,
  outline actionable implementation steps, and
  contain clear and accountable performance measures.

## Slide 4: Process
Collaborative Strategic Planning
Developed by Dr. Patrick Sanaghan over 25 years of work with more than 100 colleges and universities over the past 25 years.
Five-phase process
Designed to meaningfully engage University stakeholders with the goal of creating a shared future vision.

## Slide 5: Phase One | Getting Organized July – September 2014
Strategic Planning Team (SPT) appointed
  Faculty will comprise a majority of the SPT.
  Administrative and professional staff from the four divisions round membership.
Intensive two-day training (September 18-19) led by Dr. Sanaghan
  Training about the five phases of the process and the interactive techniques used in the next phase. Team assignments are made and a work plan is adopted.

## Slide 6: Phase Two | Engagement and Data Gathering September - November 2014
Engagement of stakeholders, both on and off campus, in discussions about the current and future challenges we face, and the critical issues we must proactively manage.
Members will use facilitated exercises designed to result in a set of prioritized issues or responses to solicit ideas and feedback about these issues.
The data generated will be compiled and posted on the Envision website.
Active engagement is key to the success of this phase of the planning process.

## Slide 7: Phase Three | Making Sense of the Issues November 21, 2014
Main goal: Identify and develop the dominant strategic themes
A thorough review and analysis of the data collected will identify strategic priorities (target: 5-10). These priorities will help focus the next phases of the process and helps prevent information overload.
Concept papers prepared on each identified strategic priority. Purpose: present the relevant issues in a clear and understandable way.

## Slide 8: Phase Four | Visioning February 2015
A vision conference (Jan. 30, 2015) will bring together diverse stakeholders, both internal and external, to review and discuss the strategic priority concept papers.
Participants then help craft a shared vision for the university's future.
SPT condenses the preferred future described by the vision conference participants into a vision statement for the university. This serves as the foundation for strategic goal and implementation plan design during the final phase.

## Slide 9: Phase Five | Goal Setting March 2015
SPT Goals Conference on March 6, 2015.
Informed by what has been learned, the SPT will draft strategic goals and proposed action plans for review by the President’s Cabinet.

## Slide 10: Next Steps April 2015 +
Board Review/Adoption
  Plan draft presented to BOR in April.
  SPT responsibilities conclude after final BOR adoption.
Implementation
  After BOR adoption, the President's Cabinet is responsible for implementation and timing of the specific actions contained in the plan.

## Slide 11: Key Dates (subject to change)
September 18-19, 2014
SPT Training
November 21, 2014
Sense-making Workshop
January 30, 2015
Vision Conference
March 6, 2015
Goal Setting Workshop